## ASE-COE Gantt Chart
Task | Start Date | End Date
ASE - Propulsion Test | 2022-02-23 | 2022-02-23 | Notes
ASE - Critical Design Review | 2022-02-23 | 2022-03-02 | All start on day and duration values are relative to the 23rd of February (ASE Propulsion Test Date)
ASE - Wing Test | 2022-03-22 | 2022-03-23
ASE - System Integration Review | 2022-03-23 | 2022-03-30
ASE - First Flight | 2022-03-30 | 2022-04-06
ASE - Engineering Flight Test | 2022-04-06 | 2022-04-14
ASE - Operational Test Flight | 2022-04-14 | 2022-04-18
ASE - Final Test Flight | 2022-04-18 | 2022-04-26
ASE - Flyoff | 2022-04-20 | 2022-04-27
ASE - System Design Review | 2022-04-27 | 2022-05-04
ATR/ADP - Preliminary Design Presentation | 2022-02-23 | 2022-02-28
ATR - Finalize Camera Model | 2022-02-25 | 2022-03-02
ATR/ADP - Preliminary Proposal Report | 2022-02-28 | 2022-03-07
ATR/ADP - Detailed Design and Analysis Plan Presentation | 2022-03-07 | 2022-03-23
ATR - Use Quadcopters to obtain Training Data | 2022-03-25 | 2022-04-01
ATR/ADP - Preliminary Results | 2022-03-28 | 2022-04-22
ATR/ADP - Final Presentations | 2022-04-11 | 2022-05-11
ATR/ADP - Final Report | 2022-05-02 | 2022-05-11
Task | Start on Day | Duration
ASE - Propulsion Test | 0 | 0
ASE - Critical Design Review | 0 | 7
ASE - Wing Test | 27 | 1
ASE - System Integration Review | 28 | 7
ASE - First Flight | 35 | 7
ASE - Engineering Flight Test | 42 | 8
ASE - Operational Test Flight | 50 | 4
ASE - Final Test Flight | 54 | 8
ASE - Flyoff | 56 | 7
ASE - System Design Review | 63 | 7
ATR/ADP - Preliminary Design Presentation | 0 | 5
ATR - Finalize Camera Model | 2 | 5
ATR/ADP - Preliminary Proposal Report | 5 | 7
ATR/ADP - Detailed Design and Analysis Plan Presentation | 12 | 16
ATR - Use Quadcopters to obtain Training Data | 30 | 7
ATR/ADP - Preliminary Results | 33 | 25
ATR/ADP - Final Presentations | 47 | 30
ATR/ADP - Final Report | 68 | 9

## COE Narrow Scope Gantt Chart
Task | Start on Day | Duration
ASE - Propulsion Test | 0 | 0 | Notes
ASE - Critical Design Review | 7 | #REF! | All start on day and duration values are relative to the 23rd of February (ASE Propulsion Test Date)
ASE - Wing Test | 27 | #REF! | Assign team members to tasks
ASE - System Integration Review | 28 | #REF!
ASE - First Flight | 35 | #REF!
ASE - Engineering Flight Test | 42 | #REF!
ASE - Operational Test Flight | 50 | #REF!
ASE - Flyoff | 56 | #REF!
ASE - System Design Review | 63 | #REF!
ATR - Preliminary Design Presentation | 0 | #REF!
ATR - Finalize Camera Model | 5 | #REF!
ATR - Preliminary Proposal Report | 5 | #REF!
ATR - Use Quadcopters to obtain Training Data | 7 | #REF!
ATR - Detailed Design Presentation | #REF! | #REF!
ATR - Analysis Plan | #REF! | #REF!
ATR - Preliminary Results | #REF! | #REF!
ATR - Final Presentations | #REF! | #REF!
ATR - Final Report | #REF! | #REF!